Five Year Plan for Coordinated Assessments

July, 2015

Introduction

The Coordinated Assessments (CA) project was begun in 2010, with the intent of making the collection, compilation, and reporting of fisheries data in the Columbia Basin, particularly that associated with the federal hydrosystem, more efficient. The project is focused on addressing standardizing regional fish data for high level indicators. The project is a collaborative effort amongst many partners, working under the direction of the NPCC Fish and Wildlife Program and largely funded by BPA.

CA initially focused on providing data to address the Viable Salmon Population (VSP) data needs of NOAA for 5 year status reviews. As data began to flow for the initial 4 indicators selected as a priority for this purpose, it became clear that a longer term plan for CA was needed. This document addresses that need.

In order to determine direction for the project, an online survey was conducted in the spring of 2015, asking respondents their opinions on a number of data management questions. Discussions were then held with the CA Core Team, StreamNet Steering Committee, BPA, NPCC, CA Planning Group, and others. In July, 2015 the StreamNet Executive Committee (representatives of the Colville Tribes, WDFW, USFWS, IDFG, MFWP, ODFW, and CRITFC) adopted this plan as an outline for the CA going forward for the next five years.

The intent is for the CA project to be a collaborative, consensus based effort. All participants, including non-StreamNet partners, are encouraged to share any concerns or issues they may have about this document or CA in general. We will attempt to address all concerns to the greatest extent possible.

Vision

High level indicators are standardized for specific regional data needs on a prioritized basis. A longer term schedule for the Coordinated Assessments Project is developed, including a general outline of when the next indicators will come on line. Close contact with HLI users (BPA, NPCC, NOAA, others) and with regional fish and wildlife managers is maintained. Collaboration and consensus is used for decision making wherever possible. Other parties (e.g. resident fish managers, habitat managers, etc.) are recruited as needed. The plan is revisited annually to ensure alignment with regional priorities, and changed as needed if regional priorities change.  Multiple tasks will occur annually; Populating last indicators with data while developing the next DES and also automating data flow for previous indicators. The plan may require additional resources to fully implement.

Existing CA Indicator Exchange Templates

Natural Origin (Adopted)

Spawner abundance (with / without jacks)

Smolt to adult ratio (percentage)

Recruits per spawner:  adults

Recruits per spawner:  juveniles

Presmolt abundance

Number of outmigrants

(Draft) Hatchery Origin

Smolt to adult ratio (percentage)

Recruits per spawner:  adults

Number of fish spawned

Proportion of hatchery broodstock that are natural origin fish

Egg take

Proportionate natural influence (PNI) of supplementation hatcheries (with / without jacks)

Egg to release survival rates for hatchery programs

Annual CA Work Template*

Maintain, update, and automate existing data flow

Finalize DES for new indicators adopted the previous year, Populate new indicators with data

Begin development of next indicators; identify a target that needs regionally standardized data, identify data category and focus of next regional data standardization under CA; involve the right people, form a DES group

Conduct Performance review; does the regional data collection and reporting effort match the need?

Year 1 (Oct, 2015 – Sep, 2016) in the CA 5 Year Plan

Maintain, update, and automate existing data flow; Maintain and automate flow for existing NO fish indicators

Finalize DES for new indicators adopted the previous year, Populate new indicators with data; Develop and finalize additional NO indicators. Identify available data and begin to populate last adopted indicators with data

Begin development of next indicators; identify a target that needs regionally standardized data, identify data category and focus of next regional data standardization under CA; involve the right people, form a DES group; Development of hatchery indicators will be slowed while a StreamNet Executive Committee  assessment of currently available data, hatchery data needs, etc. is conducted. Project will ensure alignment with regional hatchery data needs through discussion with hatchery data users and current existing hatchery database managers

Conduct Performance review; does the regional data collection and reporting effort match the need? The StreamNet Executive Committee and regional fish and wildlife managers will try and assess data availability, critical gaps, relationships to regional data needs, etc. for the CA project. To start, the review will focus on the initial 4 NO indictors and the “pHOS” and “pHEC” question. Review will include recommendations on data collection effort (i.e. more or less data collection needed for certain indicators), representative populations, resident O. mykiss in steelhead population areas, etc.

Year 2 (Oct, 2016 – Sep, 2017) in the CA 5 Year Plan

Maintain, update, and automate existing data flow; Maintain and automate flow for existing NO fish indicators. Fully populate all new NO indicators with data. Implement recommendations of Performance Review for NO indicators and data flow

Finalize DES for new indicators adopted the previous year, Populate new indicators with data; Based on the previous year’s performance review, continue development of hatchery indicators, assess available data, begin to populate hatchery indicators, coordinate closely with hatchery database managers

Begin development of next indicators; identify a target that needs regionally standardized data, identify data category and focus of next regional data standardization under CA; involve the right people, form a DES group; Re-initiate development of hatchery indicators through involvement of potentially expanded DES team

Conduct Performance review; does the regional data collection and reporting effort match the need? None

Year 3 (Oct, 2017 – Sep, 2018) in the CA 5 Year Plan

Maintain, update, and automate existing data flow; Maintain automated flow of existing NO indicators. Continue to populate and update adopted indicators with data.

Finalize DES for new indicators adopted the previous year, Populate new indicators with data; Finalize and adopt hatchery indicators. Begin to populate adopted hatchery indicators with data

Begin development of next indicators; identify a target that needs regionally standardized data, identify data category and focus of next regional data standardization under CA; involve the right people, form a DES group; Conduct review of data on lamprey, sturgeon, and bull trout, to assess and discuss data availability, critical gaps, relationships to regional data needs, etc. for the CA project. Begin development of lamprey, sturgeon, and bull trout indicators, ensure alignment with data needs, and broaden discussion to include lamprey, sturgeon, and bull trout database managers

Conduct Performance review; does the regional data collection and reporting effort match the need? Review hatchery data, flow and assess data availability, critical gaps, relationships to regional data needs, etc. for the CA project. Review will include recommendations on data collection effort (i.e. more or less data collection needed for certain indicators)

Year 4 (Oct, 2018 – Sep, 2019) in the CA 5 Year Plan

Maintain, update, and automate existing data flow; Maintain automated flow of NO and hatchery indicators and continue to populate and update adopted indicators with data. Implement recommendations of performance reviews in data collection efforts

Finalize DES for new indicators adopted the previous year, Populate new indicators with data; Finalize and adopt lamprey, sturgeon, and bull trout indicators, begin to populate with data

Begin development of next indicators; identify a target that needs regionally standardized data, identify data category and focus of next regional data standardization under CA; involve the right people, form a DES group; Conduct review of data on resident trout, to assess and discuss data availability, critical gaps, relationships to regional data needs, etc. for the CA project. Begin development of resident trout indicators, ensure alignment with data needs, and broaden discussion to resident trout database managers

Conduct Performance review; does the regional data collection and reporting effort match the need? Review lamprey, sturgeon, and bull trout data, flow and assess data availability, critical gaps, relationships to regional data needs, etc. for the CA project. Review will include recommendations on data collection effort (i.e. more or less data collection needed for certain indicators)

Year 5 (Oct, 2019 – Sep, 2020) in the CA 5 Year Plan

Maintain, update, and automate existing data flow; Maintain automated flow of NO, hatchery, lamprey, sturgeon, and bull trout indicators and continue to populate and update adopted indicators with data. Implement recommendations of performance reviews in data collection efforts

Finalize DES for new indicators adopted the previous year, Populate new indicators with data; Finalize and adopt resident trout indicators, begin to populate with data

Begin development of next indicators; identify a target that needs regionally standardized data, identify data category and focus of next regional data standardization under CA; involve the right people, form a DES group; Conduct review of CA project and evaluate next 5 years for possible new plan. Include assessment of regional data needs, etc. for the CA project (to include habitat indicator discussion, other?)

Conduct Performance review; does the regional data collection and reporting effort match the need? Review all current CA data, flow and assess data availability, critical gaps, relationships to regional data needs, etc. for the CA project. Review will include recommendations for next 5 years of the CA project

* Revisit annually and change as needed if regional priorities change. Years are Contract fiscal years (Oct. 1 – Sep. 30)