Five Year Plan for Coordinated Assessments

October, 2019 – September, 2024 (Adopted August 1, 2019)

Introduction

The Coordinated Assessments (CA) project was begun in 2010, with the intent of making the collection, compilation, and reporting of fisheries data in the Columbia Basin, particularly that associated with the federal hydrosystem, more efficient. The project is focused on addressing standardizing regional high level indicators (HLIs) for the health of fish populations. CA is a collaborative effort amongst many partners, working under the direction of the NPCC Fish and Wildlife Program and largely funded by BPA.  (A list of acronyms used is provided at the end of this document.)

CA initially focused on providing data to address the Viable Salmonid Population (VSP) data needs of NOAA for 5 year status reviews. As data began to flow for the initial 4 indicators selected as a priority for this purpose, it became clear that a longer term plan for CA was needed. This document addresses that need.

This is the second five year plan for the project. In June, 2019 the StreamNet Executive Committee (representatives of BPA, NOAA, NPCC, the Colville Tribes, WDFW, USFWS, IDFG, MFWP, ODFW, and CRITFC) discussed this plan as an outline for CA going forward for the next five years. The plan was reviewed and updated by the Committee and adopted August 1, 2019.

The intent is for the CA project to be a collaborative, consensus based effort. All participants, including non-StreamNet partners, are encouraged to share any concerns or issues they may have about this document or CA in general. We will attempt to address such concerns to the greatest extent possible.

Vision

High level indicators are prioritized, and data to meet them standardized and shared to meet specific regional needs. A longer term schedule for the CA Project is developed, including a general outline of when the next indicators will become available. Close contact with HLI users (BPA, NPCC, NOAA, others) and with regional fish and wildlife managers is maintained. Collaboration and consensus are used for decision making wherever possible. Other parties (e.g. resident fish managers, habitat managers, etc.) are recruited as needed. The plan is revisited annually to ensure alignment with regional priorities, and changed as needed if regional priorities change.

Workgroup Roles and Responsibilities

Data from the CA effort is maintained and shared via the CAX database and web site (https://cax.streamnet.org/), which is hosted by PSMFC StreamNet. StreamNet supports CA participation in its partner organizations through funding subcontracts. PNAMP maintains the historical records of CA and coordinates regional communication with the CA Distribution List. The tribal ITMD Project serves a somewhat analogous role with the CRITFC tribes to the StreamNet partners, supporting their participation in CA.

CA Core Team – The CA Core Team meets regularly to coordinate CA amongst several BPA funded projects. The Core Team is made up of representatives from BPA, PNAMP, StreamNet, a StreamNet partner agency representative, and the tribal ITMD project at CRITFC, who are directly responsible for ensuring that CA produces results. The Core team facilitates discussion amongst projects, directs requests for work to the appropriate CA level (as needed), and generally serves to maintain forward momentum. They manage and implement periodic CA Workshops, as needed.  The project history and related documents are maintained on the PNAMP website at: https://www.pnamp.org/project/coordinated-assessments-for-salmon-and-steelhead. All detailed technical documents for the CAX are available here: http://www.streamnet.org/coordinated-assessments-xct-development/

Coordinated Assessments Distribution List – The CA effort hosts periodic workshops to share updates to the DES, review high-level strategic guidance for CA, update CAX status, and broadly communicate CA activities to the region, including annual and five-year work plans. The list of invitees and participants in the workshops is maintained by PNAMP and used for the workshops and/or large scale input needed for the effort.  This is the broadest group of participants in CA.  The workshops are hosted and facilitated by PNAMP.  All agendas, documents, and meeting notes are available on the PNAMP website: https://www.pnamp.org/project/coordinated-assessments-for-salmon-and-steelhead.

StreamNet Executive Committee – This committee is made up of policy staff and project leaders from the StreamNet partner agencies as well as other related organizations involved in managing and using fisheries data, primarily in the Columbia Basin. This group provides the high-level guidance and decision-making for CA. This includes review of the high-level goals and products of the CA effort and making decisions on species, populations, indicators, and priorities on a long term and an annual basis. An invitation to the individual CRITFC tribes to join this committee has been made, and several of the tribes participate, though not consistently. The chair is the PSMFC Executive Director. All agendas, documents, and meeting notes are available on the StreamNet website: https://www.streamnet.org/resources/documents-and-publications/streamnet-executive-committee/

StreamNet Steering Committee – This committee helps to implement the decisions of the StreamNet Executive Committee, particularly as it relates to the content of the CAX.  This group includes active participation by non-StreamNet members at the data manager level. This includes NOAA and some tribal representatives. The committee is made up of technical project leaders from the StreamNet partner agencies as well as other related organizations involved in managing fisheries data, primarily in the Columbia Basin. The chair is the PSMFC StreamNet Program Manager. All agendas, documents, and meeting notes are available on the StreamNet website: https://www.streamnet.org/resources/documents-and-publications/streamnet-steering-committee/

StreamNet Technical Team – This group is composed primarily of PSMFC and state and tribal agency staff from StreamNet partners that implement data management actions. The chair is one of the PSMFC StreamNet technical experts.  This group has assumed the responsibilities formerly covered by the Exchange Configuration Team, dealing with the programming details necessary to adequately flow data from partner data systems to the CAX and other StreamNet systems.

DES Development Team (DDT) – The DDT meets as necessary to maintain existing data tables and develop new indicator tables.  This group consists of both data technicians and biologists that are responsible for calculating indicators. The DDT determines DES content and import/export guidelines. Actual team membership is fluid and depends on the species/indicators/geography of the data. New DES teams may form as the CA effort moves to other data categories, such as Bull Trout or hatcheries. The chair of the DDT is the PSMFC StreamNet biologist.  The most current DES is available on the StreamNet website at: http://www.streamnet.org/coordinated-assessments-des/.

CRITFC ITMD Project – CRITFC hosts the Inter-Tribal Monitoring Data (ITMD) project. The purpose of the ITMD is to assist CRITFC and its member tribes in the timely and accurate capture, storage, processing, and dissemination of data for management of anadromous fish and their habitats. There are four main objectives for the ITMD project:  1) Assist CRITFC and member tribes to develop cost effective computer architectures and data management strategies for anadromous fish and habitat data, 2) Provide data management services to the tribes, 3) Assist member tribes to build internal capacity for improved data management, and 4) Enable tribal participation in regional data management and coordination processes.  It is important that the ITMD Project fully coordinate and integrate appropriate activities with the CA effort to ensure consistent data sharing for Columbia Basin salmon and steelhead. The CRITFC project leader for ITMD is a member of the CA Core Team.

Existing CA Indicator Exchange Templates

The current adopted and draft HLI templates are displayed below;

| Natural Origin (Adopted) | Hatchery Origin (Draft) |
| --- | --- |
| - Spawner abundance (with / without jacks) - Smolt to adult ratio (percentage) - Recruits per spawner: adults - Recruits per spawner: juveniles - Presmolt abundance - Number of outmigrants | - Recruits per spawner: adults - Number of fish spawned - Proportion of hatchery broodstock that are natural origin fish - Egg take - Proportionate natural influence (PNI) of supplementation hatcheries (with / without jacks) - Egg to release survival rates for hatchery programs |

*Note that the hatchery Indicators are currently not being used in data collection. Further action will be dependent on additional direction from the Executive Committee

Annual CA Workflow

Maintain, update, and automate existing data flow. Maintain contact with NOAA, BPA and NPCC Fish & Wildlife Program Sponsors on data priorities and data management issues they wish to address. Facilitate problem-solving with partner agencies (and others) on an ongoing basis.

Discuss any potential new indicators with the StreamNet Executive Committee. Identify targets that might benefit from regionally standardized data, identify any data category focus of new efforts for regional data standardization under CA. If new efforts are prioritized for standardization, then involve the right people, form a DES group, clearly fill a defined need

Maintain existing DES. Finalize DES for new indicators (if any) adopted the previous year. Populate new indicators with data.

Year 1

Maintain, update, and automate existing data flow. Maintain effort for existing HLIs. Focus effort on current population priorities. Maintain data flow for existing high priority traditional data. Prioritize the capture of data from entities who have data but have not had the capacity to share it. Bonneville will identify specific BPA-funded projects where long term datasets are not in the CAX. StreamNet will facilitate attempts to obtain data and fill in data gaps in the CAX.

NOAA, BPA and the NPCC will specify any changes in data priorities, including priority populations, traditional StreamNet data series, and desired new indicators that they wish to share.

NOAA, BPA and the NPCC will identify any specific data gaps that they wish to prioritize addressing for the calendar year.

StreamNet staff will address these needs by facilitating discussion of these topics via the CA process. Once identified and coordinated, obtaining this information will become a priority. A calendar year annual report will include a report on this effort.

In addition, StreamNet will remain apprised of and will respond to overall policy direction as it is forthcoming, including:

- NPCC F&W Program Amendments

- Columbia Partnership

- Federal BiOps, EIS, etc.

StreamNet will continue to work with tribes via coordination with the tribal ITMD Project. Efforts will be targeted at DES refinement, process improvement, and data sharing efficiencies, as possible.

In year one, discussion of a potential indicator for “carrying capacity” will be initiated. This discussion will be initially limited to a “scoping exercise”. Further definition is needed regarding the purpose, methodology, and ability to calculate the carrying capacity metric across populations to determine if this is a useful indicator.  To start, BPA will describe the purpose and definitions they envision for this indicator, as well as how it would be used. Once described, StreamNet will convene a small group to describe a planned scoping exercise to develop a general outline of a carrying capacity indicator, including the metrics and data that could be used to calculate this HLI and the workload this might entail. The Executive Committee will then be briefed and asked to approve the initiation of scoping during the year.

The CA 5 year plan will be reviewed and revised annually with Executive Committee Direction.

Schedule a CA workshop if warranted.

Year 2

Maintain, update, and automate existing data flow. Maintain effort for existing HLIs. Focus effort on current population priorities. Maintain data flow for existing high priority traditional data. Prioritize the capture of data from entities who have data but have not had the capacity to share it. Obtain data and fill in data gaps in the CAX.

NOAA, BPA and the NPCC will specify any changes in data priorities, including priority populations, traditional StreamNet data series, and desired new indicators that they wish to share.

NOAA, BPA and the NPCC will identify any specific data gaps that they wish to prioritize addressing for the calendar year.

StreamNet staff will address these needs by facilitating discussion of these topics via the CA process. Once identified and coordinated, obtaining this information will become a priority. A calendar year annual report will include a report on this effort.

Follow through on the “Carrying Capacity” Indicator will be conducted if approved by the Executive Committee in Year 1. This may include development of metrics, HLIs, DES, etc. Begin data flow on this indicator (if adopted).

Conduct a scoping exercise for a White Sturgeon abundance indicator (similar to “NOSA” in salmon and steelhead).  Further definition is needed before proceeding to development. Proponents will describe the purpose of this indicator and how it would be used at a meeting of the Executive Committee. If directed to proceed, StreamNet will facilitate a scoping exercise to develop a general outline of a White Sturgeon indicator, including the metrics and data that could be used to calculate this HLI. StreamNet will then convene a small group of F&W managers to discuss and report back to the Executive Committee on possible adoption.

In addition, StreamNet will remain apprised of and will respond to overall policy direction as it is forthcoming, including:

- NPCC F&W Program Amendments

- Columbia Partnership

- Federal BiOps, EIS, etc.

StreamNet will continue to work with tribes via coordination with the tribal ITMD Project. Efforts will be targeted at DES refinement, process improvement, and data sharing efficiencies, as possible.

Finalize DES for new indicators adopted the previous year (if any). Populate new indicators with data.

Schedule a CA workshop if warranted.

The CA 5 year plan will be reviewed and revised annually with Executive Committee direction, including consideration of any new indicators or data groups.

Year 3

Maintain, update, and automate existing data flow. Maintain effort for existing HLIs. Focus effort on current population priorities. Maintain data flow for existing high priority traditional data. Prioritize the capture of data from entities who have data but have not had the capacity to share it. Obtain data and fill in data gaps in the CAX.

NOAA, BPA and the NPCC will specify any changes in data priorities, including priority populations, traditional StreamNet data series, and desired new indicators that they wish to share.

NOAA, BPA and the NPCC will identify any specific data gaps that they wish to prioritize addressing for the calendar year.

StreamNet staff will address these needs by facilitating discussion of these topics via the CA process. Once identified and coordinated, obtaining this information will become a priority. A calendar year annual report will include a report on this effort.

In addition, StreamNet will remain apprised of and will respond to overall policy direction as it is forthcoming, including:

- NPCC F&W Program Amendments

- Columbia Partnership

- Federal BiOps, EIS, etc.

StreamNet will continue to work with tribes via coordination with the tribal ITMD Project. Efforts will be targeted at DES refinement, process improvement, and data sharing efficiencies, as possible.

Finalize DES for new indicators adopted the previous year.

Populate new indicators with data.

Schedule a CA workshop if warranted.

The CA 5 year plan will be reviewed and revised annually with Executive Committee direction, including consideration of any new indicators or data groups.

Year 4

Maintain, update, and automate existing data flow. Maintain effort for existing HLIs. Focus effort on current population priorities. Maintain data flow for existing high priority traditional data. Prioritize the capture of data from entities who have data but have not had the capacity to share it. Obtain data and fill in data gaps in the CAX.

NOAA, BPA and the NPCC will specify any changes in data priorities, including priority populations, traditional StreamNet data series, and desired new indicators that they wish to share.

NOAA, BPA and the NPCC will identify any specific data gaps that they wish to prioritize addressing for the calendar year.

StreamNet staff will address these needs by facilitating discussion of these topics via the CA process. Once identified and coordinated, obtaining this information will become a priority. A calendar year annual report will include a report on this effort.

In addition, StreamNet will remain apprised of and will respond to overall policy direction as it is forthcoming, including:

- NPCC F&W Program Amendments

- Columbia Partnership

- Federal BiOps, EIS, etc.

StreamNet will continue to work with tribes via coordination with the tribal ITMD Project. Efforts will be targeted at DES refinement, process improvement, and data sharing efficiencies, as possible.

Finalize DES for new indicators adopted the previous year. Populate new indicators with data.

Schedule a CA workshop if warranted.

The CA 5 year plan will be reviewed and revised annually with Executive Committee direction, including consideration of any new indicators or data groups.

Year 5

Maintain, update, and automate existing data flow. Maintain effort for existing HLIs. Focus effort on current population priorities. Maintain data flow for existing high priority traditional data. Prioritize the capture of data from entities who have data but have not had the capacity to share it. Obtain data and fill in data gaps in the CAX.

NOAA, BPA and the NPCC will specify any changes in data priorities, including priority populations, traditional StreamNet data series, and desired new indicators that they wish to share.

NOAA, BPA and the NPCC will identify any specific data gaps that they wish to prioritize addressing for the calendar year.

StreamNet staff will address these needs by facilitating discussion of these topics via the CA process. Once identified and coordinated, obtaining this information will become a priority. A calendar year annual report will include a report on this effort.

In addition, StreamNet will remain apprised of and will respond to overall policy direction as it is forthcoming, including:

- NPCC F&W Program Amendments

- Columbia Partnership

- Federal BiOps, EIS, etc.

StreamNet will continue to work with tribes via coordination with the tribal ITMD Project. Efforts will be targeted at DES refinement, process improvement, and data sharing efficiencies, as possible.

Finalize DES for new indicators adopted the previous year. Populate new indicators with data.

The CA 5 year plan will be reviewed and revised annually with Executive Committee direction, including consideration of any new indicators or data groups.

Schedule a CA workshop if warranted.

Conduct review of CA project and update / develop a new plan for next 5 years. Include assessment of regional data needs

List of Acronyms

BiOp		Biological Opinion

BPA		Bonneville Power Administration

CA		Coordinated Assessments

CAX	Coordinated Assessments Exchange.  The online Coordinated Assessments query system at https://cax.streamnet.org.

CRITFC		Columbia River Intertribal Fish Commission

- DDT		DES Development Team

- DES		Data Exchange Standard

- EIS		Environmental Impact Statement

- HLI		High Level Indicator

- IDFG		Idaho Department of Fish and Game

ITMD	Inter-Tribal Monitoring Data.  A project lead by CRITFC to improve the ability of the CRITFC member tribes to manage and share data. The purpose of the ITMD project is to assist CRITFC and its member tribes in the timely and accurate capture, storage, processing, and dissemination of data for management of anadromous fish and their habitats.

- MFWP		Montana Fish, Wildlife & Parks

NOAA	National Oceanic and Atmospheric Administration, National Marine Fisheries Service

- NOSA		Natural Origin Spawner Abundance.  (The number of fish that actually spawn.)

- NPCC		Northwest Power and Conservation Council

- ODFW		Oregon Department of Fish and Wildlife

- PNAMP	Pacific Northwest Aquatic Monitoring Partnership

- PSMFC		Pacific States Marine Fisheries Commission

- USFWS		U.S. Fish and Wildlife Service

- WDFW		Washington Department of Fish and Wildlife